## Sheet1
Marcus, Sara, Brett | DATE | ID | VALUE | TASK (STORY) | WHO DOES WHAT TASK | ESTIMATED HRS. | ACTUAL HRS. | LOGGING ERRORS
| 2020-02-17 | 1 | 5 | Market research | Everyone | 10
|  | 2 | 5 | Research user interface and menu button | Everyone | 13
|  | 3 | 5 | Research how to create a drop-down menu for category page |  | 10
|  | 4 | 5 | Create a category page(drop down menu) |  | 10
|  | 5 | 5 | Design menu button |  | 13
|  | 6 | 5 | Create user interface |  | 10
|  | 7 | 2 | Research how to create login page |  | 10
|  | 8 | 3 | Design screenlayout for login page |  | 13
|  | 9 | 3 | Code the login page |  | 10
|  | 10 | 5 | Test login page |  | 10
|  | 11 | 5 | Research how to design account page |  | 10
|  | 12 | 2 | Design screenlayout for account page |  | 12
|  | 13 | 1 | Code the account page |  | 10
|  | 14 | 1 | Test account page |  | 10
|  | 15 | 1 | Research how to create admin page |  | 10
|  | 16 | 5 | Design screenlayout for admin page |  | 10
|  | 17 | 3 | Code the admin page |  | 10
|  | 18 | 3 | Test admin page |  | 13
|  | 19 | 3 | Logo implementation |  | 10
|  | 20 | 3 | Research how to create a contacts page |  | 10
|  | 21 | 2 | Design a contacts page |  | 10
|  | 22 | 2 | Research how to create a drop-down menu for category page |  | 10
|  | 23 | 2 | Database creation |  | 10
|  | 24 | 2 | Product backlog: allow user to reset password |  | 10
|  | 25 | 2 | allow user to edit items |  | 10
|  | 26 | 2 | allow user to create a report of data |  | 10
|  | 27 | 2 | allow user to update reminder settings when a product is added |  | 10
|  | 28 | 2 | As an unauthorized user, create a new account |  | 10
|  | 29 | 2 | As an unauthorized user, login to the account |  | 10
|  | 30 | 4 | As an authorized user, I want to log out of the account |  | 10
|  | 31 | 3 | As an authorized user, I want to see the list of items so I can select one. |  | 10
|  | 32 | 3 | As an authorized user, I want to add a new item so it appears on list. |  | 10
|  | 33 | 3 | As an authorized user, I want to delete an item off my list. |  | 10
|  | 34 | 3 | As an authorized user, I want to edit the quantity. |  | 10
|  | 35 |  | As an admin, I want to see a list of accounts on login
PEER REVIEW EACH TASK